# Enki — Prototype Pre-Deployment Security Plan

Critical-tier work items for first-customer readiness

SDI · KingOfTheGeeks

2026-05-02

Table of Contents

# Enki — Prototype Pre-Deployment Security Plan

| Field | Value |
| --- | --- |
| Document number | SDI-ENG-PLAN-001 |
| Document type | Engineering Plan |
| Version | 1.1 |
| Status | Draft |
| Effective date | 2026-05-02 |
| Document owner | Mike King |
| Related docs | SDI-ENG-SOP-002 (Authorization), SDI-ENG-SOP-004 (Security Testing), docs/Enki-Permissions-Matrix.docx, docs/deploy.md |

# 0. Executive summary

This plan covers the Critical-tier security work that must complete before a first prototype customer can sign in to Enki. The original top-five list from the May 2026 access-control review has been verified against current code: two items (license-generation audit, admin role-flip audit) are already implemented and have been removed. The remaining real work is three workstreams plus one verification pass:

| # | Workstream | Effort | Order | Blocks customer access? |
| --- | --- | --- | --- | --- |
| A | Phase 5b auth UX (forgot-password + email confirmation) | 7–10 dev-days | Last (depends on email infra) | Yes — admin-driven password resets don’t scale to a paying customer |
| B | File-upload hardening (content-type, magic-byte, filename sanitisation) | 3–5 dev-days | Mid | Yes — exposes shot/log endpoints to malformed binaries |
| C | Secrets management + deploy-guide finalisation (env-vars only for SDI-hosted; Phase 2 customer-hosted left open) | ~2 dev-days | First | Yes — production must not boot from appsettings.json |
| D | Sensitive-op audit verification (every privileged op is captured) | 0.5 dev-day | First (parallel with C) | No — defensive, but cheap |

Total effort: approximately 12–18 dev-days for one engineer focused. Splittable across two engineers as workstreams C+D parallel with B, then both feed into A.

Out of scope (explicitly deferred to High-tier or later): TOTP MFA, centralised logging, rate limiting on tenant-content writes, force-password-change on first login, idle-session timeout. See the prior security review hand-off for the full High-tier list.

# 1. Verified-before-planning

Two items from the original Critical list have been verified as already implemented. They are out of scope for this plan and must remain in place — any regression on them re-promotes them to Critical.

## 1.1 License generation / revocation audit

Status: implemented. License (in src/SDI.Enki.Core/Master/Licensing/License.cs) implements IAuditable. Every Create / Update / Delete on the entity is captured by EnkiMasterDbContext’s audit interceptor and written to MasterAuditLog. Verified by inspection 2026-05-02.

Regression detector: SOP-004 SEC-8.10-003 (Joel generates a license) followed by a master-audit feed check should show a row. Add a SOP-004 row asserting this if the regression risk is real.

## 1.2 Admin role-flip audit

Status: implemented. AdminUsersController.SetAdmin (src/SDI.Enki.Identity/Controllers/AdminUsersController.cs:548-591) writes a RoleGranted / RoleRevoked row via WriteAuditAsync after the column flip. The audit row appears in the Identity audit feed (/admin/audit/identity). Verified by inspection 2026-05-02.

Regression detector: an admin flips another user’s IsEnkiAdmin column → row appears in /admin/audit/identity. Worth one SOP-004 row.

# 2. Workstream C: Secrets management + deploy guide

Goal. A production deployment of Enki must not source any secret from a committed appsettings.*.json file. Connection strings, the OIDC signing-cert password, the seed user password, and the OIDC client secret all flow through IConfiguration; the production deploy must wire that abstraction to a vault.

## 2.1 Current state

The three host Program.cs files read every secret through IConfiguration already — the abstraction is correct. What’s missing is:

- No documented inventory of every required secret, its environment-variable form, and where it’s loaded from in production.

- appsettings.Development.json carries dev secrets (see Server=localhost;...;Password=5q!@dm1n1str@t0r;... in src/SDI.Enki.Identity/appsettings.Development.json:14). These are dev-only and must NEVER ship in a release branch’s appsettings.{Production}.json or equivalent.

- No startup validation that required secrets are present in non-Development. A missing env var silently falls through to a default (sometimes a hard-coded dev fallback), which is dangerous.

## 2.2 Design — phased approach

The deployment scenario informs the choice. Two phases:

Phase 1 (current): Enki is hosted on SDI’s own servers behind SDI’s firewall. A single ops team controls every host. Secrets sourcing is uniform: environment variables set on each host’s service registration. No vault product. No external dependency.

Phase 2 (future): Enki may be deployed to customer-hosted infrastructure. Customers vary in their secret-management preferences: some run HashiCorp Vault, some have their own corporate KMS, some have nothing at all. To avoid locking SDI into a single vault product (or forcing every customer onto SDI’s choice), the architecture stays deliberately open: customers extend the standard IConfiguration provider chain at deploy time with whatever their environment supports. SDI’s build remains free of any vault dependency.

Why no vault now, even though SDI controls the infrastructure. Running HashiCorp Vault (or equivalent) introduces operational complexity — sealing/unsealing, backup, HA topology, key recovery runbooks — before there’s a problem that demands it. Env vars give auditable change history through the deploy scripts (which live in git). When auditor pressure, rotation requirements, or per-secret access logs become real needs, that’s the moment to introduce a vault. Until then, simpler is better.

Provider chain in each host’s Program.cs — already wired by ASP.NET Core defaults, but explicit ordering documented:

1. appsettings.json
2. appsettings.{Environment}.json
3. environment variables (ENKI_ prefix)            ← production secret source
4. command-line arguments

Customers in Phase 2 plug their provider into step 3 or 4 by editing their fork’s Program.cs (or via a partial-class extension hook — deferred until an actual customer ask).

## 2.3 Tasks

| ID | Task | Files | Depends on | Effort |
| --- | --- | --- | --- | --- |
| C-01 | Inventory every required secret (configuration key, env-var name, what it secures) | grep across src/; cross-check appsettings.*.json | — | 0.5d |
| C-02 | Confirm AddEnvironmentVariables is in each host’s config chain (probably already is via ASP.NET defaults — verify) | src/*/Program.cs (3 files) | — | 0.25d |
| C-03 | Add startup validation: fail loud in non-Development when any required secret is missing | src/*/Program.cs | C-01 | 0.5d |
| C-04 | Rewrite docs/deploy.md Secret staging section: env-var contract, secret inventory table, Phase 2 future-proofing notes | docs/deploy.md | C-01 | 0.5d |
| C-05 | Smoke test: each host boots with all secrets in env vars and zero secrets in appsettings.*.json | scripted in scripts/ | C-02, C-03 | 0.25d |

## 2.4 Test strategy

- Unit: trivial — no business logic added.

- Integration: the smoke test in C-05 is the meaningful coverage: appsettings.Production.json carries no secrets, all values come from env vars, host boots cleanly. Re-run on every release.

- Negative: delete a required env var, boot host, confirm it fails loud at startup (with the missing key name in the message), rather than silently falling through to a default or a dev fallback.

## 2.5 Risks and unknowns

- Dev seed fallback exposure. Identity:Seed:DefaultUserPassword carries the dev fallback Enki!dev1 in the seeder. The C-03 startup validation must reject any path where this fallback is reachable in non-Development — otherwise a customer install with the seed env var unset could ship a host with a known password.

- Phase 2 customer extensibility — deferred, not solved. Customers who want their own vault will fork Program.cs to add their provider. This is acceptable for the foreseeable future; if customer demand consolidates around one or two patterns (e.g. several customers with HashiCorp Vault), introduce a partial-class ApplyCustomerProviders hook at that point.

## 2.6 Acceptance criteria

- A1: Every secret in C-01’s inventory has an entry in docs/deploy.md.

- A2: All three hosts boot in a Production environment with zero secrets in appsettings.*.json.

- A3: Removing any required secret produces a fail-loud startup error, not a silent fall-through.

- A4: docs/deploy.md reviewed and signed off by the Document Owner.

# 3. Workstream D: Sensitive-op audit verification

Goal. Every privileged operation in the system writes a row to one of the audit feeds (master / identity / auth-events). This is a verification pass, not new development — known-implemented ops were proven during the May 2026 review (license generation, admin role flip), but a comprehensive sweep has never been done.

## 3.1 Approach

For every controller action gated by a non-EnkiApiScope policy (i.e. every privileged operation), confirm one of:

- The action’s entity implements IAuditable (interceptor-captured); OR

- The action explicitly calls WriteAuditAsync / equivalent; OR

- The action is read-only and intentionally not audited.

Document the sweep result in a table; raise issues for gaps.

## 3.2 Tasks

| ID | Task | Effort |
| --- | --- | --- |
| D-01 | Enumerate every controller action gated by a non-EnkiApiScope policy | 0.25d |
| D-02 | Categorise each action (interceptor-captured / explicit-audit / read-only) | 0.25d |
| D-03 | File issues for any privileged write that is NOT captured | 0d (deliverable) |

## 3.3 Acceptance criteria

- A1: A table is committed to docs/audit-coverage-matrix.md listing every privileged action and its audit shape.

- A2: Any gap identified in D-03 is either fixed or filed as an accepted-known-issue with a tracked backlog item.

## 3.4 Risks

Likely outcome: zero gaps. The IAuditable + interceptor pattern is broadly applied. The cost of confirming this is small (half a day) and the benefit is a defensible audit-coverage statement when a customer auditor asks.

# 4. Workstream B: File-upload hardening

Goal. Every binary upload endpoint must reject malformed, oversized, or hostile uploads before the bytes reach domain code or storage. Today size limits are enforced; content-type, magic-byte verification, and filename sanitisation are not.

## 4.1 Endpoints in scope

Four binary-upload endpoints at the WebApi layer:

| Endpoint | Verb | Controller | Notes |
| --- | --- | --- | --- |
| /tenants/{c}/jobs/{j}/runs/{r}/shots/{s}/binary | POST | ShotsController.UploadBinary | Primary tool binary, ≤250 KB |
| /tenants/{c}/jobs/{j}/runs/{r}/shots/{s}/gyro-binary | POST | ShotsController.UploadGyroBinary | Gyro tool binary |
| /tenants/{c}/jobs/{j}/runs/{r}/passive/binary | POST | RunsController.UploadPassiveBinary | Passive run binary |
| /tenants/{c}/jobs/{j}/runs/{r}/logs/{l}/binary | POST | LogsController.UploadBinary | Log capture binary |

## 4.2 Current state

For each endpoint:

| Hardening | Status |
| --- | --- |
| RequestSizeLimit attribute | ✓ enforced (per-endpoint cap) |
| Explicit length check (defence-in-depth) | ✓ on Shots; verify on Runs/Logs |
| ContentType allow-list | ✗ accepts any content type |
| Magic-byte / signature verification | ✗ not validated |
| Filename sanitisation | ✗ filename stored verbatim from IFormFile.FileName |
| Storage isolation | ✓ stored as varbinary in tenant DB (no filesystem path) |
| Audit on upload | partial — uploads are EF-tracked (interceptor catches the row mutation) but no explicit “binary uploaded” event |

## 4.3 Design

Layer 1 — request-shape validation (per controller action): - Reject if IFormFile.Length == 0 (already done on Shots). - Reject if Length > MaxBinaryBytes (already done). - Reject if IFormFile.ContentType not in { "application/octet-stream" } (the AMR binary class). New. - Reject if IFormFile.FileName contains path separators (/, \), control characters, or NUL. New.

Layer 2 — content validation (centralised): - A BinaryFormatValidator service inspects the first N bytes against a known-good signature for the AMR binary format. Reject on mismatch. - The signature is provided by the Marduk team (or extracted from a representative sample) — discovery item.

Layer 3 — storage: - Use Path.GetFileName(file.FileName) defensively even though we don’t write to disk, so any future filesystem migration doesn’t silently re-introduce the gap.

Out of scope: - Antivirus scanning. Mark as a High-tier item; route through ICAP or a cloud AV when customer compliance demands it. - Re-encoding / format conversion server-side.

## 4.4 Tasks

| ID | Task | Files | Effort |
| --- | --- | --- | --- |
| B-01 | Confirm length-check on RunsController.UploadPassiveBinary and LogsController.UploadBinary matches Shots pattern; add if missing | RunsController.cs, LogsController.cs | 0.5d |
| B-02 | Centralise content-type allow-list as a constant in EnkiBinaryUploadDefaults (Shared) | new file in SDI.Enki.Shared | 0.25d |
| B-03 | Add content-type guard to all four endpoints | each controller | 0.5d |
| B-04 | Filename sanitiser utility (single-source) | SDI.Enki.Shared | 0.25d |
| B-05 | Apply sanitiser to all four endpoints | each controller | 0.5d |
| B-06 | Discovery: obtain the AMR binary-format magic-byte signature from Marduk | conversation + sample bytes | 0.25d |
| B-07 | Implement BinaryFormatValidator service + DI registration | SDI.Enki.Infrastructure | 0.5d |
| B-08 | Wire validator into all four endpoints | each controller | 0.5d |
| B-09 | Test coverage: ContentType reject, oversized reject, magic-byte reject, filename sanitisation | tests/SDI.Enki.WebApi.Tests/Controllers/* | 1.0d |
| B-10 | SOP-004 update: add binary-upload negative-path tests under §8.8 | docs/sop-security-testing.md | 0.25d |

## 4.5 Test strategy

- Unit: ContentType allow-list, filename sanitiser, BinaryFormatValidator.

- Integration: Each upload endpoint is exercised with: valid binary (passes), wrong ContentType (415), oversized (413), wrong magic bytes (400), filename with / (400).

- Manual: SOP-004 §8.8 gains 4 new rows under Field+Tenant rig writes (or a dedicated subsection if more).

## 4.6 Risks

- Magic-byte unknown. B-06 might surface that the AMR binary format doesn’t have a stable header — in which case fall back to length + content-type validation only, and document the limitation.

- Backward compatibility. Older binaries already in tenant DBs may not match the new format check. The validator only runs on uploads, not on existing rows.

## 4.7 Acceptance criteria

- A1: Every endpoint in §4.1 rejects each of: empty file, oversized, bad ContentType, bad filename, bad magic bytes.

- A2: Test suite covers all 4 negative paths × 4 endpoints (16 new tests).

- A3: SOP-004 §8.8 reflects the new tests.

- A4: Manual penetration probe (see Workstream A in High-tier) confirms no untested gap.

# 5. Workstream A: Phase 5b auth UX

Goal. Customers must be able to recover access without contacting SDI. This requires a self-service password-reset flow and an email-confirmation flow. Both depend on a working email service.

## 5.1 Current state

ASP.NET Identity in the Identity host already supports the underlying primitives (UserManager.GeneratePasswordResetTokenAsync, GenerateEmailConfirmationTokenAsync). What’s missing:

- No IEmailSender implementation. Identity’s default no-op sender silently swallows email requests.

- No public Razor pages for /Account/ForgotPassword, /Account/ResetPassword?token=…, /Account/ConfirmEmail?token=…, /Account/ResendConfirmation.

- Admin-created users have EmailConfirmed = true (verify in IdentitySeedData and AdminUsersController.Create). Customers never proved their email.

- No SMTP configuration in appsettings.*.json.

- No rate limiting on the new public endpoints (open spam target).

## 5.2 Design

### 5.2.1 Email service

Abstraction: IEnkiEmailSender with one method:

Task SendAsync(string to, string subject, string htmlBody, string textBody, CancellationToken ct);

Two implementations: - SmtpEnkiEmailSender — production, configured by Email:Smtp:* keys (host, port, credentials from vault per Workstream C). - LogOnlyEnkiEmailSender — Development. Writes the email body to Serilog and a file under logs/dev-emails/. Lets dotnet test and the dev rig exercise the flow without spamming.

DI: registered via AddEnkiEmailSender() extension that picks the implementation based on environment. Followed pattern from existing AddEnkiInfrastructure.

### 5.2.2 Forgot-password flow

Public Razor pages on the Identity host:

- GET /Account/ForgotPassword — form with email field.

- POST /Account/ForgotPassword — accept email, look up user. Always return the same success page regardless of whether the email exists (prevents email enumeration). If user exists and their EmailConfirmed = true, generate a token via UserManager.GeneratePasswordResetTokenAsync and email a link containing it.

- GET /Account/ResetPassword?email=…&token=… — form with two new-password fields.

- POST /Account/ResetPassword — accept submission, call UserManager.ResetPasswordAsync, force security-stamp rotation (invalidates other sessions), redirect to /Account/Login with a success banner.

Token TTL. Identity’s default is 24 hours; set explicitly via DataProtectionTokenProviderOptions.TokenLifespan for clarity.

Rate limiting. Add to the existing OIDC rate-limit policy: /Account/ForgotPassword is partitioned per-IP and per-email, allowing 3 requests / 5 min / partition.

Audit. - PasswordResetRequested row written on every form submission (regardless of whether the email exists, for forensics). - PasswordResetCompleted on success.

### 5.2.3 Email-confirmation flow

Initial-state policy: - New users created by admin: EmailConfirmed = false. - The user can sign in immediately (don’t block initial sign-in — the admin handed off a temp password and the user has to set their own). - A persistent banner on the home page reads “Please confirm your email — Send confirmation link”. Clicking that calls POST /Account/ResendConfirmation (signed-in only). - Forgot-password flow is denied for users with EmailConfirmed = false (return the same generic success page so there’s no enumeration leak, but no email is sent).

Public Razor page on the Identity host:

- GET /Account/ConfirmEmail?userId=…&token=… — calls UserManager.ConfirmEmailAsync, redirects to /Account/Login with a success banner.

Authenticated endpoint (Identity host):

- POST /me/resend-confirmation (or /Account/ResendConfirmation) — any signed-in user can request a resend for their own email. Rate limited at 1 / 60 sec / user.

Audit. - EmailConfirmationRequested on resend. - EmailConfirmed on success.

Seed migration. IdentitySeedData stamps every seeded user with EmailConfirmed = true so dev workflows are unaffected.

### 5.2.4 First-login UX

Add a banner check in the Blazor home page: - If User.HasClaim("email_verified", "false") (claim materialised by EnkiUserClaimsPrincipalFactory), render the banner. - The banner is dismissible per session but reappears on next sign-in until confirmed.

## 5.3 Tasks

| ID | Task | Files | Depends on | Effort |
| --- | --- | --- | --- | --- |
| A-01 | IEnkiEmailSender interface | SDI.Enki.Shared | — | 0.25d |
| A-02 | SmtpEnkiEmailSender implementation | SDI.Enki.Identity | C-01 (vault for SMTP creds) | 0.5d |
| A-03 | LogOnlyEnkiEmailSender (dev) + DI selector | SDI.Enki.Identity | A-01 | 0.25d |
| A-04 | IEmailSender ASP.NET Identity adapter (delegates to IEnkiEmailSender) | SDI.Enki.Identity | A-01 | 0.25d |
| A-05 | SMTP configuration keys in appsettings.json (template) and deploy.md | both | C-04 | 0.25d |
| A-06 | Razor page: /Account/ForgotPassword (GET + POST) | SDI.Enki.Identity/Pages/Account/ | A-02 | 0.5d |
| A-07 | Razor page: /Account/ResetPassword (GET + POST) | SDI.Enki.Identity/Pages/Account/ | — | 0.5d |
| A-08 | Email template (HTML + text) for password reset | SDI.Enki.Identity/EmailTemplates/ | A-01 | 0.25d |
| A-09 | Rate limit on /Account/ForgotPassword (per-IP and per-email) | SDI.Enki.Identity/Program.cs | — | 0.25d |
| A-10 | Audit rows for PasswordResetRequested / PasswordResetCompleted | SDI.Enki.Identity/Data/AuthEventLogger | — | 0.25d |
| A-11 | Razor page: /Account/ConfirmEmail | SDI.Enki.Identity/Pages/Account/ | A-02 | 0.25d |
| A-12 | Endpoint: POST /me/resend-confirmation | SDI.Enki.Identity/Controllers/MeController.cs | A-02 | 0.25d |
| A-13 | Email template for confirmation | SDI.Enki.Identity/EmailTemplates/ | — | 0.25d |
| A-14 | Audit rows for EmailConfirmationRequested / EmailConfirmed | as A-10 | — | 0.25d |
| A-15 | EnkiUserClaimsPrincipalFactory projects email_verified claim | SDI.Enki.Identity/Data/EnkiUserClaimsPrincipalFactory.cs | — | 0.25d |
| A-16 | Blazor home-page banner for unconfirmed email | SDI.Enki.BlazorServer/Components/Pages/Home.razor | A-15 | 0.5d |
| A-17 | Banner on Blazor calls POST /me/resend-confirmation via the existing EnkiIdentity HttpClient | as A-16 | A-12 | 0.25d |
| A-18 | Update seeders: IdentitySeedData sets EmailConfirmed = true for dev users | SDI.Enki.Identity/Data/IdentitySeedData.cs | — | 0.25d |
| A-19 | Update AdminUsersController.Create: new users get EmailConfirmed = false | SDI.Enki.Identity/Controllers/AdminUsersController.cs | — | 0.25d |
| A-20 | Integration tests: full forgot-password flow (request, click link, set password, sign in) | tests/SDI.Enki.Identity.Tests/ | A-06, A-07 | 1.0d |
| A-21 | Integration tests: email confirmation flow | tests/SDI.Enki.Identity.Tests/ | A-11, A-12 | 0.5d |
| A-22 | Integration tests: enumeration-leak prevention (forgot-password returns same page for known/unknown email) | tests/SDI.Enki.Identity.Tests/ | A-06 | 0.5d |
| A-23 | SOP-004 update: new §8.17 covering forgot-password, §8.18 covering email confirmation | docs/sop-security-testing.md | A-22 | 0.5d |

## 5.4 Test strategy

Unit: - Email service contract (mock SMTP, verify message shape). - Token TTL enforced. - Filename sanitiser (cross-cutting).

Integration (Identity.Tests project): - Forgot-password happy path. - Forgot-password to unknown email returns success page (no enumeration). - Forgot-password to unconfirmed-email user returns success page, no email sent. - Reset-password with expired token returns error. - Reset-password with token from a different user returns error. - Email-confirmation happy path. - Resend-confirmation rate limit (>1/min returns 429). - Forgot-password rate limit (>3/5min returns 429).

Manual (SOP-004): - New §8.17 — forgot-password. - New §8.18 — email confirmation.

## 5.5 Risks

- Email deliverability. SMTP-from-customer-server may land in spam. For prototype, accept that. Long-term: SPF/DKIM/DMARC records on the customer’s domain, or route through a transactional email provider (SendGrid, Postmark, etc.). Track as a Medium-tier item.

- Token-leak via referrer header. Reset-password URLs carry the token in the query string. If the user clicks an external link from the reset page, the referrer leaks the token. Mitigation: set Referrer-Policy: no-referrer on the reset page response.

- Existing sessions on other devices. When a password is reset, the security stamp rotates; OpenIddict tokens issued for that user become invalid on the next API call (returns 401). The user is bounced to login. This is the desired behaviour — document it in release notes.

## 5.6 Acceptance criteria

- A1: A user can complete the forgot-password flow end-to-end without contacting SDI.

- A2: A user can confirm their email after admin-created account.

- A3: All integration tests in §5.4 pass.

- A4: SOP-004 §8.17 + §8.18 added; pass on first run against the delivered build.

- A5: No email-enumeration leak (test §5.4 confirms).

# 6. Sequencing

Day 0 ───► Workstream C (secrets) ──► Workstream D (audit verify)
                │                            │
                ▼                            │
            (vault key for SMTP)             │
                │                            │
                ▼                            ▼
            Workstream A (auth UX) ◄──── Workstream B (uploads)
                                            (parallel)
                │
                ▼
           SOP-004 update + run ──► sign-off

Why this order:

- C first because secrets management is decoupled from feature code — finishing it early lets later workstreams use vault-sourced values from day 1, especially the SMTP credentials Workstream A needs.

- D in parallel with C because the audit-coverage sweep is read-only across the codebase — no merge conflicts with C’s host startup edits.

- B in parallel with A once C is done. B has zero dependencies on A; the two engineers can split.

- A last (or final) because it’s the largest workstream, depends on email infra (which depends on C’s vault for SMTP creds), and the integration tests need the most stable foundation.

## 6.1 Critical path

The earliest feasible “ready for first prototype customer” date is: - Single engineer: C → D → B → A, ~14 dev-days serial. - Two engineers: {C+D} | B → A with the second engineer starting B on day 2 (after C finishes), ~10 dev-days end-to-end.

## 6.2 Definition of done for “prototype-ready”

When all four workstreams’ acceptance criteria are met, plus:

- A full SOP-004 run (now expanded with §8.17 + §8.18 + 16 new upload-rejection rows) is recorded against the candidate build with zero Fail rows.

- A pen-test sweep (out-of-band, ~1 dev-day) confirms no obvious gap.

- The deploy guide (docs/deploy.md) documents every secret and the vault key path for the chosen target.

# 7. Tracking

Each task ID in this plan (e.g. A-07, B-04, C-03, D-01) becomes a GitHub issue with the prefix in the title. Issues link back to this document. The plan version increments each time the task list changes; new versions are tagged in source control alongside the release that consumed them.

| Tracking artefact | Where |
| --- | --- |
| Master plan (this document) | docs/plan-prototype-security.md |
| Per-task issues | GitHub Issues, prefixed [SEC-PLAN] {task-id}: {title} |
| Release tag for “prototype-ready” | v0.X-prototype-ready |
| SOP-004 expanded run record | docs/test-runs/{date}-{commit}-sec.md |

# 8. Out of scope (deferred)

These items came up during the May 2026 review but are deferred to High-tier work, after this plan completes. Listed here so the trail of decisions is visible:

- TOTP MFA (at minimum for IsEnkiAdmin users).

- Centralised log shipping (Seq / Application Insights / ELK).

- Rate limiting on tenant-content writes (DoS surface on /tenants/{c}/runs/{r}/shots/{s}/binary).

- Force password change on first sign-in.

- Idle session timeout.

- CSP / HSTS / CORS final lockdown.

- Append-only audit log (hash-chain or off-DB shipping).

- Anomaly detection on auth events.

- Bug-bounty / responsible disclosure programme.

# 9. Document control

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | 2026-05-02 | Mike King | Initial issue. Scoped against the May 2026 access-control review with two original Critical items (license-audit, admin-flip-audit) verified as already implemented and removed from the plan. |
| 1.1 | 2026-05-02 | Mike King | Workstream C revised. Decision: SDI hosts on its own infrastructure for the foreseeable future, with possible migration to customer-hosted environments later. Vault-target selection collapsed — Phase 1 uses environment variables only (no vault product, no external dependency); Phase 2 (customer-hosted) leaves the door open for customers to plug their own secret-management tooling into the standard IConfiguration chain. C-02 and C-03 retired; effort estimate dropped from 1–2d to ~2d total. |

End of plan.